## Slide 1: G2P Installation Readiness

## Slide 2: Fast raster & Calorimeter

## Slide 3: Upside down girder

## Slide 4: FZ magnets

## Slide 5: Target platform

## Slide 6: Target Platform security
Prex Radcon security fence
Gates
Interlocked magnetic locks
Warning beacons
E stop button
Bolted on window covers

## Slide 7: Septum Magnet
In place
Pre aligned
Power shielding installed
Water lines tested
Working on OSPs for power up

## Slide 8: Power supplies
Have begun operational checkout of
Big Box
HKS
FZ 1
FZ 2

## Slide 9: Beam Dump
Lead parts here
Inserts are here
Tungsten here with issues to resolve

## Slide 10: Third arm
Being assembled

## Slide 11: Experiment OSPs
Slow Raster operation and testing Being written
FZ magnets operation and testing Complete
FZ 2 magnet positioning and alignment Being written
Target operation and testing In review
HKS power supply operation and testing In review
Big Box power supply operation and testing In review
Septum magnet operation and testing In review
Septum magnet mapping Being written
Lower balcony access for third arm access In review
Beam dump insert removal and replacement In review

## Slide 12: Concerns
Survivability of target magnet
Radiation levels at local beam dump

## Slide 13: Questions?