## Sheet1
Estimated SoLID offline computing effort
10-Sep-2018
v3

Simulations
Task	Group	FTE	FTE	FTE	FTE	To	Subtotals
		weeks	weeks	weeks	weeks	Staff/	required
		Labs	universities	non-DOE	optional	Ops

Physics generators	ANL	12			12
Magnet & support geometry	JLab, ANL	4
GEMs	UVa, Temple
Geometry			4
Digitization			4		8
LGC	Temple
Geometry			2
Digitization			4		2
HGC	Duke
Geometry			2
Digitization			4		2
ECAL	UVa, W&M
Geometry			4
Digitization			4		8
MRPC	China
Geometry				2
Digitization				4
Digitization testing		10			10
DAQ/Trigger emulation	JLab	16
Framework integration	ANL	8
Code testing/QA	ANL	6
Activities coordination	ANL	12				12
					-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
Subtotal Simulations					102

Reconstruction
Framework	JLab
Build system		3
ROOT tree output module		6
Multi-threading
Distributed architecture					12
Documentation		8			8
Database API & integration	JLab
Geometry		4
Conditions		4
Mapping		2
Requirements determination	JLab
Data model	JLab	4
Tracking	Duke, JLab
GEM cluster analysis		3	3
GEM track finding SIDIS, J/Psi		12	12
GEM track finding PVDIS		6	6
GEM track fitting		4	4
Calorimeter cluster finding	UVa/W&M, JLab	6	2
Cherenkov amplitude analysis		2
MRPC ToF analysis	China			2
Overall PID framework	JLab	4
Event display	JLab	8
EVIO raw data decoder	JLab	12
Slow Controls integration	JLab				16
Testing/QA	JLab	12			24
Activities coordination	JLab	12				12
					-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
Subtotal Reconstruction					141

Calibrations	overall estimate:		50
GEM tracker alignment	(including validations)
GEM data QA
Calorimeter gains
Cherenkov PMT gains & timing
MRPC time calibration
Activities coordination			12			12
					-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
Subtotal Calibrations					62

Production & Data Quality
Detector optimization MC	ANL, univ	12	12
Physics studies MC	ANL, univ	12	6
Farm workflow, including L3	JLab	12			12
Production coordination	JLab	12				12
Production monitoring, validation	JLab	15
					-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
Subtotal Production					81

Analysis
PVDIS baseline replay			8			8
SIDIS-3He baseline replay			12			12
SIDIS-p baseline replay			6			6
J/Psi baseline replay			6			6
Coordination/meetings			12			12
Analysis code QA			6		6	6
					-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
Subtotal Analysis					50

Data Challenges
3 offline challenges		12
L3 farm commissioning		2
					-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
					14
		-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
Sum		257	185	8	120	98	450
		57%	41%	2%
Contingency	0%	0	0	0		0	0
		-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
Sum with contingency		257	185	8	120	98	450
Developer efficiency	75%
(overhead for training
and collecting requirements)
Overhead from efficiency		86	62	3	40	33	150
		-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
Total estimated effort		343	247	11	160	131	600
Overall total (req'd + optional)					760

Simulation and reconstruction only		240	73	11	136	32	324
					460