## Sheet1
Estimated SoLID offline computing effort
10-Sep-2018
v3

Simulations
Task	Group	FTE	FTE	FTE	To	FTE	Subtotals
		weeks	weeks	weeks	Staff/	weeks	required
		Labs	universities	non-DOE	Ops	optional

Physics generators	ANL	12				12
Magnet & support geometry	JLab, ANL	4
GEMs	UVa, Temple
Geometry			4
Digitization			4			8
LGC	Temple
Geometry			2
Digitization			4			2
HGC	Duke
Geometry			2
Digitization			4			2
ECAL	UVa, W&M
Geometry			4
Digitization			4			8
MRPC	China
Geometry				2
Digitization				4
Digitization testing		10				10
DAQ/Trigger emulation	JLab	16
Framework integration	ANL	8
Code testing/QA	ANL	6
Activities coordination	ANL	12			12
					-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
Subtotal Simulations					102

Reconstruction
Framework	JLab
Build system		3
ROOT tree output module		6
Multi-threading
Distributed architecture					12
Documentation		8				8
Database API & integration	JLab
Geometry		4
Conditions		4
Mapping		2
Requirements determination	JLab
Data model	JLab	4
Tracking	Duke, JLab
GEM cluster analysis		3	3
GEM track finding SIDIS, J/Psi		12	12
GEM track finding PVDIS		6	6
GEM track fitting		4	4
Calorimeter cluster finding	UVa/W&M, JLab	6	2
Cherenkov amplitude analysis		2
MRPC ToF analysis	China			2
Overall PID framework	JLab	4
Event display	JLab	8
EVIO raw data decoder	JLab	12
Slow Controls integration	JLab					16
Testing/QA	JLab	12				24
Activities coordination	JLab	12			12
					-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
Subtotal Reconstruction					141

Calibrations	overall estimate:		50
GEM tracker alignment	(including validations)
GEM data QA
Calorimeter gains
Cherenkov PMT gains & timing
MRPC time calibration
Activities coordination			12		12
					-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
Subtotal Calibrations					62

Production & Data Quality
Detector optimization MC	ANL, univ	12	12
Physics studies MC	ANL, univ	12	6
Farm workflow, including L3	JLab	12				12
Production coordination	JLab	12			12
Production monitoring, validation	JLab	15
					-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
Subtotal Production					81

Analysis
PVDIS baseline replay			8		8
SIDIS-3He baseline replay			12		12
SIDIS-p baseline replay			6		6
J/Psi baseline replay			6		6
Coordination/meetings			12		12
Analysis code QA			6		6	6
					-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
Subtotal Analysis					50

Data Challenges
3 offline challenges		12
L3 farm commissioning		2
					-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
					14
		-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
Sum		257	185	8	98	120	450
		57%	41%	2%
Contingency	25%	64	46	2	25	30	113
		-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
Sum with contingency		321	231	10	123	150	563
Developer efficiency	75%
(overhead for training
and collecting requirements)
Overhead from efficiency		107	77	3	41	50	188
		-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-	-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
Total estimated effort		428	308	13	163	200	750
Overall total (req'd + optional)					950

Simulation and reconstruction only		300	92	13	40	170	405
					575