## Sheet1
Estimated SoLID offline computing effort
1-Dec-2016
v2

Simulations
Task	Group	FTE		Scaled FTE-
		weeks		weeks

Physics generators	SBU	24
Magnet & support geometry	JLab, ANL	4
GEMs	UVa, Temple
Geometry		4
Digitization		12
LGC	Temple
Geometry		2
Digitization		6
HGC	Duke
Geometry		2
Digitization		6
ECAL	UVa, W&M
Geometry		4
Digitization		12
MRPC	China
Geometry		2
Digitization		4
Digitization testing		20
DAQ/Trigger emulation	JLab	16
Framework integration	JLab	8
Code testing/QA		6
Activities coordination	Duke	12
			-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-​-
Subtotal Simulations			144	240

Reconstruction
Framework	JLab
Build system		3
ROOT tree output module		6
Multi-threading		12
Distributed architecture		12
Documentation		16
Database API & integration	JLab
Geometry		4
Conditions		4
Mapping		2
Requirements determination	JLab
Data model	JLab	4
Tracking	Duke, JLab
GEM cluster analysis		6
GEM track finding SIDIS, J/Psi		24
GEM track finding PVDIS		12
GEM track fitting		8
Calorimeter cluster finding	UVa, JLab	8
Cherenkov amplitude analysis		2
MRPC ToF analysis		2
Overall PID framework	JLab	4
Event display	JLab	8
EVIO raw data decoder	JLab	12
Slow Controls integration	JLab	16
Testing/QA	JLab	36
Activities coordination	JLab	12
			-
Subtotal Reconstruction			213	355

Calibrations	overall estimate:	50
GEM tracker alignment	(including validations)
GEM data QA
Calorimeter gains
Cherenkov PMT gains & timing
MRPC time calibration
Activities coordination		12
			-
Subtotal Calibrations			62	103

Production & Data Quality
Detector optimization MC		24
Physics studies MC		18
Farm workflow, including L3		24
Production coordination		12
Production monitoring, validation		15
			-
Subtotal Production			93	155

Analysis
PVDIS baseline replay		8
SIDIS-3He baseline replay		12
SIDIS-p baseline replay		6
J/Psi baseline replay		6
Coordination/meetings		12
Analysis code QA		16
			-
Subtotal Analysis			60	100

Data Challenges
3 offline challenges		12
L3 farm commissioning		2
			-
			14	23
			-
Sum			586

Contingency	25%		147
			-
Sum with contingency			733
Developer efficiency	75%
(overhead for training
and collecting requirements)
Overhead from efficiency			244
			-
Total estimated effort			977	976