## Sheet1
Estimated SoLID offline computing effort
2016-12-01
v2
Simulations
Task | Group | FTE |  | Scaled FTE-
|  | weeks |  | weeks
Physics generators | SBU | 24
Magnet & support geometry | JLab, ANL | 4
GEMs | UVa, Temple
Geometry |  | 4
Digitization |  | 12
LGC | Temple
Geometry |  | 2
Digitization |  | 6
HGC | Duke
Geometry |  | 2
Digitization |  | 6
ECAL | UVa, W&M
Geometry |  | 4
Digitization |  | 12
MRPC | China
Geometry |  | 2
Digitization |  | 4
Digitization testing |  | 20
DAQ/Trigger emulation | JLab | 16
Framework integration | JLab | 8
Code testing/QA |  | 6
Activities coordination | Duke | 12
-
Subtotal Simulations |  |  | 144 | 240
Reconstruction
Framework | JLab
Build system |  | 3
ROOT tree output module |  | 6
Multi-threading |  | 12
Distributed architecture |  | 12
Documentation |  | 16
Database API & integration | JLab
Geometry |  | 4
Conditions |  | 4
Mapping |  | 2
Requirements determination | JLab
Data model | JLab | 4
Tracking | Duke, JLab
GEM cluster analysis |  | 6
GEM track finding SIDIS, J/Psi |  | 24
GEM track finding PVDIS |  | 12
GEM track fitting |  | 8
Calorimeter cluster finding | UVa, JLab | 8
Cherenkov amplitude analysis |  | 2
MRPC ToF analysis |  | 2
Overall PID framework | JLab | 4
Event display | JLab | 8
EVIO raw data decoder | JLab | 12
Slow Controls integration | JLab | 16
Testing/QA | JLab | 36
Activities coordination | JLab | 12
-
Subtotal Reconstruction |  |  | 213 | 355
Calibrations | overall estimate: | 50
GEM tracker alignment | (including validations)
GEM data QA
Calorimeter gains
Cherenkov PMT gains & timing
MRPC time calibration
Activities coordination |  | 12
-
Subtotal Calibrations |  |  | 62 | 103
Production & Data Quality
Detector optimization MC |  | 24
Physics studies MC |  | 18
Farm workflow, including L3 |  | 24
Production coordination |  | 12
Production monitoring, validation |  | 15
-
Subtotal Production |  |  | 93 | 155
Analysis
PVDIS baseline replay |  | 8
SIDIS-3He baseline replay |  | 12
SIDIS-p baseline replay |  | 6
J/Psi baseline replay |  | 6
Coordination/meetings |  | 12
Analysis code QA |  | 16
-
Subtotal Analysis |  |  | 60 | 100
Data Challenges
3 offline challenges |  | 12
L3 farm commissioning |  | 2
-
|  |  | 14 | 23
-
Sum |  |  | 586
Contingency | 25% |  | 146.5
-
Sum with contingency |  |  | 732.5
Developer efficiency | 75%
(overhead for training
and collecting requirements)
Overhead from efficiency |  |  | 244.1667
-
Total estimated effort |  |  | 976.6667 | 976