## Slide 1
Thia Keppel
6/4/13
Hall A Update

## Slide 2: Near term accelerator schedule – same as last meeting
Accelerator Run II: Beam in hall 3/2014, or maybe as early as 1/2014 (?)
  > 1.1 GeV/pass, 3 pass spin-up to Hall A
  up to 5.5 pass to D by ~5/14
  Shut down 5/3/14
Accelerator Run III: 8/30/14 – 12/1/14
  CD4A milestones
    12 GeV 5.5 pass capable installed
    11 GeV 5 pass to A, B, C installed
    > 2 nA 2.2 GeV single pass transported
  Plan
    E > 2 GeV/pass, 10 GeV to Hall D
    2 Hall operation
Accelerator Run IV: 2/13/15 – 6/1/15
  E > 2 GeV/pass, 2 hall operation
  CD4B Halls B,C,D operational, > 6, 6, 10 GeV
    Schedule rebaseline likely – won’t effect Hall A or accelerator
Physics Run I: 8/30/15 – 12/23/15
  E > 2 GeV/pass
Physics Run II: 2/6/16 – 6/25/16
Physics Run III: 9/12/16 – 12/22/16
Spring, fall, spring, fall runs continue….
Rebaselining might carry some changes, but unlikely to effect SBS

## Slide 3: Hall A Projected Experiment Schedule as of 8/2012 - available on Hall A wiki
February - May | August – December | February - June | August - December | February - June | September - December
GMp / DVCS – I (APEX) | GMp / DVCS - I |  |  |  | 
 |  | 3H/3He (A1n) | PREX (APEX) |  | 
 |  |  |  | A1n (SBS) (DVCS-II) (APEX) | SBS (A1n) (DVCS-II) (APEX)
MOLLER, SOLID…?....
2014
2016
2015
SBS
Experiments in parentheses represent potential schedule changes.
Run Period

## Slide 4: General Hall near term thoughts for SBS
Hall A should see first beam in less than ~1 year 
  Upgrade and infrastructure work underway
    Beamline – energy, current, position, polarimetry,…
    HRS’s – detector upgrades and general refurbishing
    Many things to do and help appreciated!
Experiments using ~standard equipment scheduled initially
  Allows for parallel efforts preparing for new equipment (3He target, PREX, SBS,….MOLLER,….)

## Slide 5: SBS Current Activities
10/1/12 SBS “Program” started with DOE
  Subset of the proposed physics program (magnet and GEMs)
Hall A currently supporting “pre-R&D” and SBS-related work
  3He target development (Gordon Cates)
  GEM tracker prototyping at UVA (Nilanga Liyanage)
  Hadron calorimeter (Gregg Franklin) Fermilab scintillator purchase approved

## Slide 6: SBS Design and Engineering (See Robin’s talk!)
Yoke modification drawings ~30% complete
Design work ongoing for magnet counter weight support, will incorporate movement of support to relocate magnet
Design details of rollers, jack mounts, magnet bracket, floor plates ongoing, ~65% complete
Detailed drawings of new coils ~25%
Power supply specification completed, in procurement
Layout and design of shielded beampipe and vacuum snout ~20%
Defining field clamps and design of clamp supports ~15%
Detector support design ~20%
Mid-June delivery expected for magnet from BNL
GEn
GMn

## Slide 7: Other Thoughts
New PAC procedures for no-additional-beamtime-needed requests
  Does the SBS collaboration anticipate experiments like this?
  If so, suggest working on a process for review

## Slide 8
Looks on track for first SBS run in 2016 or 2017!