## Slide 1: Hall A 12 GeV experiments overview

## Slide 2: Hall A Projected Experiment Schedule, updated 1/2017 Experiments in red represent PAC42 “high impact” experiments
Spring | Fall | Spring | Fall | Spring | Fall
DVCS –I/ GMp | DVCS –I/ GMp |  |  |  | 
 |  | Ar(e,e’p)* | 3H/3He group |  | 
 |  |  |  | 3H/3He group | TBD: APEX PREX12 CREX A1n DVCSII
CY
2016
CY 2017
CY
2018
*possible best effort
SBS 2019?
MOLLER, SoLID 
schedule not final
2
List of approved and feasible
experiments

## Slide 3: Possible schedule
 |  | Spring | Fall
2017 |  |  | Tritium
2018 | SoLID MIE | Tritium | Tritium
2019 | SoLID funding starts | PREX ? | CREX ?
2020 |  | APEX ? | 
2021 |  | GMn ? | GEn ?
2022 |  | Gep ? | 
2023 |  | Moller ? | Moller ?
2024 |  | SoLID ? | SoLID ?
2025 |  | … | …
2026 |  | … | …
switch to CODA 3 ?

## Slide 4: DAQ milestones
SoLID Science review : November December 2017
Gen, Gep readiness review : 2017 2018
GMp ready : 2019
Gen, GEp ready : 2020

## Slide 5: DAQ Development for SBS
 | Rough date | Item | Priority
GMn - GEn | 2019-2021 | GEM VTP readout | like
 |  | GEM readout and reduction | should
GEp5 | 2020-2022 | Fastbus switching | must
 |  | GEM readout and reduction | must
 |  | HCAL trigger geometry matching | must
 |  | GEM VTP readout | Should ( must )

## Slide 6: Development for SoLID
DAQ deadtime Nov 2017
GEM readout rate capability and data reduction
Cerenkov readout
TOF readout
FADC VTP readout
DAQ performance
PVDIS trigger ( clustering with adjacent blocks)
New cost and document for MIE submission in 2018