## Slide 1: Hall A DAQ status and upgrade plans
Alexandre Camsonne
Hall A Jefferson Laboratory
Hall A collaboration meeting
June 10th 2011

## Slide 2: Outline
HRS DAQ upgrade
  Motivation
  Current
  Possible trigger layout
  Timeline
  Intel VME CPU
  CAMAC
Future experiments
  Pipelined electronics
  Fastbus
  L3 Farm
Summary

## Slide 3: HRS DAQ upgrade motivations
Upgrade rate capability and deadtime : current rate limited to 4 KHz at about 15 % dead time
CAMAC modules obsolete : replace with NIM and VME
High resolution TDC 1875 replacement
http://hallaweb.jlab.org/equipment/daq/daq_12gev.pdf

## Slide 4: Current HRS

## Slide 5: Possible trigger layout
TS
+
Scalers
VME VXS
VME VXS
NIM
NIM
NIM
Delay
Replace CAMAC by VME/VXS
Keep usual trigger for for compatibility
Split signal to pipelined electronics for recording and digital trigger
S1m
S2m
Cerenkov
To FADC
To FADC
To FADC
AMP
S
Delay
Logic
Delay
Logic
triggers
Delay
Discr
Other HRS trigger
L1A for other arms electronics

## Slide 6
Ben Raydo’s
Talk

## Slide 7: HRS 12 GeV Hall A DAQ upgrade milestones
Milestone Planned completion
Test 1190 and 1290 TDCs on HRS Oct-11
Implement Fastbus upgrade with Intel Quad cpus Nov-11
Complete the Design of Test Stand for Pipelined Electronics Dec-11
Obtain prototype TIR boards, new ROC and EB components for CODA 3 Jan-12
Complete the Design of the Delay Modules (Ben Raydo) Feb-12
Parts for Test Stand Delivered (FADC, TDCs, TIR, etc) Mar-12
Test of Delay Module Prototype Completed Apr-12
Initial Testing of Pipelined Electronics, informing final design May-12
Preliminary Design of DAQ and Trigger Jun-12
Order Delay Modules and other Trigger Modules Jul-12
Completed Tests of Pipeline Electronics Aug-12
Final Design of DAQ and Trigger Sep-12
Order ADCs and TDCs (at this point, looks like Jlab FADC and CAEN 1190) Oct-12
Order Crate Trigger Supervisor, Subsystem Decision Modules, etc. Nov-12
Order Fibers and Gigabit Ethernet Dec-12
All DAQ and Trigger modules delivered Jan-13
Analysis Software Upgrades Completed (based on Test Stand) Feb-13
Assembly of Full DAQ System Complete Mar-13
Preliminary Tests of Full DAQ System Apr-13
Final Tests of Full DAQ System May-13

## Slide 8: Intel VME CPUs
Dual Core CPU
Running Linux
Deploy infrastructure for operating
Support from DAQ group : Bryan Moffit and David Abbott Fastbus library adapted for the new CPU
CPUs ordered and will be tested this summer
Possible improvement of rate capability by a factor of 2 will be tested for g2p

## Slide 9: CAMAC replacement
Lecroy 4518 delay module
  Development by Jlab electronics group
Lecroy 4413 discriminator
  JLAB VME discriminator available
    16 channels
    2 outputs with two different thresholds
    Or output
    Possibility to implement logic
MLU 2373
  CAEN V1495 : multipurpose FPGA logic module
  very versatile logic but need to be careful for accurate timing

## Slide 10: Future experiments
SuperBigBite
  GEM
  Fastbus
DVCS
  Calorimeter
  Analog sampling electronics
SoLID
  Fully pipelined electronics
  L3 Farm

## Slide 11: Pipelined electronics
Continuous readout of data
No dead time
Fully digital logic
  Digital sum and trigger generation for calorimeter / scintillators
Drawbacks
  need fully pilelined to take full advantage of DAQ
  L1A latency of 2 us
Possibilty to use as regular ADC with look back in time
( No more delay lines )

## Slide 12: Pipelined electronics
JLAB FADC 250
  Flash ADC 12 bit 250 MHz 16 channels
  VXS option for summing and triggering purpose
Jlab F1 TDC
CAEN V1190
CAEN V1290
APV25 GEM readout : 40 MHz
DAQ group will handle event repacking from the block of events

## Slide 13: Fastbus
Large amount of channels available
Will be used for SuperBigBite
Drawback no pipelining/ event blocking
20 Mb/seconds transfer rate
Sufficient for low rate experiments
Might benefit from new Intel VME CPU

## Slide 14: L3 Farm
For data reduction for SoLID maybe SBS
Do treatment of event for data reduction : expect factor of 5 reduction of data amount
Need to implement test bench
  Choose algorithms : coarse reconstruction, look up table, coincidence between detectors to optimize speed and data reduction
  Determine efficiency and systematical effects

## Slide 15: Summary
HRS DAQ upgrade ongoing by stage
Support legacy electronics while allowing fully pipelined operation
New electronics being tested in different setups
Availability of 100 KHz rate capabilities for future experiments
HRS upgrade is building block of DAQ for future large experiment SBS and SoLID