## Slide 1
Hugh Montgomery
Hall A Meeting, June 2013
Jefferson Lab 12 GeV

## Slide 2: 12 GeV White Paper
arXiv:1208.1244
1 Executive Summary
2 Meson Spectroscopy, Hybrid Mesons & Confinement
3 The Internal Structure of Hadrons
4 QCD and Nuclei
5 The Standard Model and Beyond
6 Appendix A: Experimental Equipment

## Slide 3: NSAC Implementation Recommendations
“……..was unanimous in endorsing the modest-growth budget scenario as the minimum level of support that is needed to maintain a viable long-term U.S. nuclear science program that encompasses the vision of the LRP (Long Range Plan).“
“………, the subcommittee has considered the impact on the U.S. nuclear science program under three different budget scenarios. Two of them provide no growth. …….. recommendations that were made for these different scenarios must be viewed as a snapshot in time that reflects the state of the field today. …………. under all scenarios we must capitalize on the investment that has been made to upgrade CEBAF."

## Slide 4: 12 GeV Upgrade Project
Scope of the project includes:
Doubling the accelerator beam energy
New experimental Hall and beamline
Upgrades to existing Experimental Halls
Maintain capability to deliver lower pass beam energies: 2.2, 4.4, 6.6….
New Hall
Add arc
Enhanced capabilities
in existing Halls
Add 5 cryomodules
Add 5 cryomodules
20 cryomodules
20 cryomodules
Upgrade arc magnets
and supplies
CHL upgrade
Upgrade is designed to build on existing facility: vast majority of accelerator and experimental equipment have continued use
The completion of the
12 GeV Upgrade of CEBAF was ranked the highest priority in the 2007 NSAC Long Range Plan.

## Slide 5: 12 GeV Upgrade CHL Components

## Slide 6: 12 GeV Upgrade

## Slide 7: 12 GeV Upgrade New Cryomodules

## Slide 8: 12 GeV Upgrade Accelerator

## Slide 9: 12 GeV Upgrade Hall B
Sub-System Processor SSP
PCAL - cosmic ray testing
HTCC - tooling for mirror assembly
R3 DC – Two crew stringing
SVT – First pre-production module at FNAL
FTOF – Testing refurbished CLAS detectors
CTOF–Testing the fast scintillators
Space Frame

## Slide 10: 12 GeV Upgrade Hall C

## Slide 11: 12 GeV Upgrade Hall D

## Slide 12: 12 GeV Upgrade Magnets

## Slide 13
12 GeV Upgrade Project Lehman Review
Project Progress
  Review very positive
    Progress in accelerator
    Progress in physics detectors
    Progress in physics sc magnets
      Residual risks in sc magnets
      Need for continued and enhanced attention
      Attracted the bulk of the recommendations
Estimate To Complete
  Successfully established, review very positive about the work
  Recommended to proceed to implement the proposed rebaseline
Plan
  August 9, Mini-review to check on progress on recommendations
  September 1, implementation

## Slide 14
Hall D & Counting House
12 GeV Upgrade Project Status
Project 77% Complete, 91% Obligated
Civil (92%); Accelerator (91%); Physics Equip (~62%)
Challenges with spectrometer superconducting magnets
All 7 new magnets under contract
Refurbished Hall D Solenoid; further testing in progress
Rebaseline meeting scheduled for August 9, 2013
Implementation date September 1, 2013
TPC = $338M; CD-4B March 2017
Hall D Interior

## Slide 15
    Present expectation (subject to rebaseline approval in August):
    16-month installation
    May 2012 - Sept 2013
    Accelerator commissioning start Oct 2013
    Hall A commissioning start Feb 2014
    Hall D commissioning start
    Oct 2014
    Halls B & C commissioning start Jan/Feb 2016
    Project Completion March 2017
FY12: reduction of $16M
FY13: Pres Request – no restoration
Information based on
DOE Project Review
May 7-9, 2013
12 GeV Upgrade Project Schedule

## Slide 16: Beyond 12 GeV Upgrade
Super BigBite Spectrometer
(FY13-16 construction)
- High Q2 form factors
- SIDIS
MOLLER experiment
(MIE – FY15-18?)
- Standard Model Test
SoLID
Chinese collaboration
CLEO Solenoid?
Enhancements of equipment in B, C, D
(Leverage external investments)

## Slide 17
BNL “g-2” expt: Dam(expt-thy) = (287 ± 80) x 10-11 (3.6 s)
No evidence for SUSY at LHC (yet)
Another solution: A’, a massive neutral vector boson
- also useful for dark matter models
3 Jefferson Lab proposals:
New Opportunity: Search for A’ at Jefferson Lab
APEX test run (Hall A) – published
PRL 107, 191804 (2011)
HPS test run (Hall B) – complete
DarkLight test run (FEL) – complete

## Slide 18: Summary
FY2013 Budget has been a challenge
Long Range Implementation Report from NSAC
  Supported modest growth scenario for Nuclear Physics
  Recommended completing and exploiting CEBAF Upgrade under any budget scenario
NSAC Future Facilities Report for input to Office of Science
  Viewed Electron Ion Collider as central with significant R&D needed this is input to DOE/SC & likely needs a new SC1
Upgrade Project is moving forward
  Rebaselining review May 2013
  Path forward defined
  Accelerator Commissioning Fall 2013
Working on a bright and exciting future at Jefferson Lab

## Slide 19
Technology Engineering and Design Facility
TEDF building fully occupied
Test Lab Renovation on-track for completion 6 months ahead of schedule

## Slide 20: Infrastructure – UIM (SLI)
Project TEC $29.2M
  Funding FY14-15
Accelerator Site Electric Distribution Replacement
  Critical Elements Planned start 3rd Qtr FY14
  Remaining Elements Planned start 2nd Qtr FY15
Accelerator Site Cooling Towers
  Critical Elements Planned start 3rd Qtr FY14
  Planned start 2rd Qtr FY15
Cryogenic Test Facility Upgrade
  Planned Start 1st Qtr FY15
Computer center cooling and uninterruptable power supply upgrade
  Planned Start 2nd Qtr FY15
Communications Infrastructure Upgrade
  Planned Start 2nd Qtr FY15

## Slide 21: Budgets/Sequestration
 | FY09 | FY10 | FY11 | FY12 Approp Reallocated | FY13 Proposed Reallocation | FY14 Guidance Reallocated
Accelerator Operations | 47,420 | 46,080 | 44,426 | 45,140 | 39,916 | 51,383
SRF R&D | 1,635 | 1,365 | 2,421 | 2,100 | 2,050 | 2,141
Accelerator Facility Capital | 130 | 200 | 200 |  |  | 725
Accelerator Improvement Projects | 650 | 1,050 | 1,050 | 622 | 2,600 | 2,145
Experimental Facility Operations | 24,559 | 25,967 | 27,150 | 27,920 | 27,500 | 27,970
Experimental Facility Capital | 4,500 | 6,605 | 5,250 | 250 | 2,400 | 4,480
GPP | 1,800 | 2,000 | 2,516 | 2,000 | 2,500 | 2,000
Subtotal NP Facility Ops | 80,694 | 83,267 | 83,013 | 78,032 | 76,966 | 90,844
ME Research | 6,150 | 6,200 | 6,495 | 7,050 | 7,330 | 6,852
Theory Research | 3,400 | 3,699 | 4,000 | 3,900 | 4,000 | 3,873
12 GeV | 28,623 | 20,000 | 35,928 | 50,000 | 43,072 | 30,000
LQCD & SciDAC | 751 | 638 | 1,149 | 1,244 | -100 | 300
Total NP Base and 12 GeV | 119,618 | 113,804 | 130,585 | 140,225 | 131,268 | 131,869

## Slide 22: 12 GeV Upgrade Rebaseline Proposal

## Slide 23: NSAC Facilities Recommendations: Input to SC!!
Existing Facilities:
  ATLAS at ANL, RHIC at BNL, CEBAF 12 GeV at Jefferson Lab
  All considered to be absolutely central to the physics of the next decade
Future facilities:
  FRIB at NSCL
  1 tonne-scale neutrinoless bb decay
  Electron Ion Collider
  FRIB considered central and ready to build, others considered central but with significant R&D and/or engineering before ready for construction.
DOE/SC will prioritize …………

## Slide 24
Medium Energy EIC@JLab

## Slide 25: The Landscape of EIC
12 GeV
With 12 GeV we study mostly the valence quark component
An EIC aims to study gluon dominated matter.
mEIC
EIC

## Slide 26: Recent Documents

## Slide 27: EIC Realization Imagined
Assumes endorsement for an EIC at the next NSAC Long Range Plan
Assumes relevant accelerator R&D for down-select process done around 2016
Activity Name | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
12 GeV Upgrade |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FRIB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
EIC Physics Case |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NSAC LRP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
EIC CD0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
EIC Machine Design/R&D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
EIC CD1/Downsel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
EIC CD2/CD3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
EIC Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 28: Back-ups