## Sheet1
# Days since HAPPEX end	Note	Date (estimate)	Day of week	% towards completion	Beam	Left HRS angle	Left HRS p0	time	Right HRS angle	Right HRS p0	time	surveys needed	Notes
1	switchover	10/29/09	Thursday
2	switchover	10/30/09	Friday										install DAQ
3	switchover	10/31/09	Saturday										install DAQ
4	switchover	11/01/09	Sunday			12.9	-3.66		20.0	-2.63			DAQ checkout
5	switchover	11/02/09	Monday									both HRS angles, Left before 11/25, right before 12/19
6	commissioning	11/03/09	Tuesday		6.068	12.9	-3.66		20.0	-2.63
7	commissioning	11/04/09	Wednesday
8	commissioning	11/05/09	Thursday
9	commissioning	11/06/09	Friday
10		11/07/09	Saturday	0.00	6.068	12.9	-3.66	432 hours	20.0	-2.63	1507 hours
11		11/08/09	Sunday	2.17				18 days			63 days
12		11/09/09	Monday	4.35				LD2			LD2
13		11/10/09	Tuesday	6.52				7 hours			25 hours
14		11/11/09	Wednesday	8.70				dummy			dummy
15		11/12/09	Thursday	10.87
16		11/13/09	Friday	13.04
17		11/14/09	Saturday	15.22
18		11/15/09	Sunday	17.39
19		11/16/09	Monday	19.57
20		11/17/09	Tuesday	21.74
21		11/18/09	Wednesday	23.91
22		11/19/09	Thursday	26.09
23		11/20/09	Friday	28.26
24		11/21/09	Saturday	30.43
25		11/22/09	Sunday	32.61
26		11/23/09	Monday	34.78
27		11/24/09	Tuesday	36.96
28		11/25/09	Wednesday	39.13		12.9	+3.66	5 hours
29		11/26/09	Thursday	41.30		20.0	-2.63					LHRS angle (must before 12/17)
30		11/27/09	Friday	43.48
31		11/28/09	Saturday	45.65
32		11/29/09	Sunday	47.83
33		11/30/09	Monday	50.00
34		12/01/09	Tuesday	52.17
35		12/02/09	Wednesday	54.35
36		12/03/09	Thursday	56.52
37		12/04/09	Friday	58.70
38		12/05/09	Saturday	60.87
39		12/06/09	Sunday	63.04
40		12/07/09	Monday	65.22
41		12/08/09	Tuesday	67.39
42		12/09/09	Wednesday	69.57
43		12/10/09	Thursday	71.74
44		12/11/09	Friday	73.91
45		12/12/09	Saturday	76.09
46		12/13/09	Sunday	78.26
47		12/14/09	Monday	80.43
48		12/15/09	Tuesday	82.61
49		12/16/09	Wednesday	84.78
50		12/17/09	Thursday	86.96		20.0	+2.63	5 hours
51		12/18/09	Friday	89.13		14.0	-4.00	20 hours
52		12/19/09	Saturday	91.30	4.868	12.5	-4.00	28 hours	19.0	-2.77	45 hours
53		12/20/09	Sunday	93.48		12.9	-3.55	43 hours
54		12/21/09	Monday	95.65					12.9	-3.10	total >=60 hours
55		12/22/09	Tuesday	97.83		12.9	-3.10	til the end
56		12/23/09	Wednesday	100.00	4.868
57	down	12/24/09