## Sheet1
# Days since HAPPEX end	Plan	Date (estimate)	Day of week	% towards completion	Beam Energy	Left HRS angle	Left HRS p0	time	Right HRS angle	Right HRS p0	time	surveys or tech support needed	Notes
1	switchover	10/29/09	Thursday
2	switchover	10/30/09	Friday										install DAQ
3	switchover	10/31/09	Saturday										install DAQ
4	switchover	11/01/09	Sunday			12.9 (DIS#1)	-3.66		20 (DIS#2)	-2.63			DAQ checkout
5	switchover	11/02/09	Monday									both HRS angles, Left before 11/25, right before 12/19
6	commissioning	11/03/09	Tuesday		6.068	12.9	-3.66		20.0	-2.63
7	commissioning	11/04/09	Wednesday
8	commissioning	11/05/09	Thursday
9	commissioning	11/06/09	Friday
10		11/07/09	Saturday	0.00
11	First day of actual production	11/08/09	Sunday	2.27	6.068	12.9	-3.66	432 ->384 hours	20.0	-2.63	1507->1368 hours
12		11/09/09	Monday	4.55				18->16 days			63->57 days
13		11/10/09	Tuesday	6.82				LD2			LD2
14		11/11/09	Wednesday	9.09				15 hours 50uA on Al dummy (4% of LD2 time for a 0.4% endcap error)			55 hours 50uA on Al dummy (4% of LD2 time for a 0.4% endcap error)
15		11/12/09	Thursday	11.36
16		11/13/09	Friday	13.64
17		11/14/09	Saturday	15.91
18		11/15/09	Sunday	18.18
19		11/16/09	Monday	20.45
20		11/17/09	Tuesday	22.73
21		11/18/09	Wednesday	25.00
22		11/19/09	Thursday	27.27				5 hours on Al dummy done, 10 hours to go			5 hours on Al dummy done, 50 hours to go
23		11/20/09	Friday	29.55
24		11/21/09	Saturday	31.82
25		11/22/09	Sunday	34.09				9 hours on Al dummy done, 6 hours to go			9 hours on Al dummy done, 46 hours to go
26	Positron Running, spot change	11/23/09	Monday	36.36		12.9	+3.66 then change to -3.66	data taking at +3.66 is >5 hours, now up to 9 hours		+2.63 then change to -2.63	data taking at +2.63 is >5 hours, now up to 9 hours	tech changes polarity on both arms starting 12noon, then change them back 8am on Tuesday.
27		11/24/09	Tuesday	38.64
28		11/25/09	Wednesday	40.91				13 hours on Al dummy, 2 hours to go			42 hours on Al dummy, 2 hours to go
29		11/26/09	Thursday, Thanksgiving Day	43.18
30		11/27/09	Friday	45.45
31		11/28/09	Saturday	47.73
32		11/29/09	Sunday	50.00
33		11/30/09	Monday	52.27
34	Transverse Running	12/01/09	Tuesday	54.55				8 hours setup plus 16 hours data taking				invasive to Hall B, need MCC support	could be done earlier, it depends on MCC and Hall B.
35	Mini spin dance plus Left arm kinematics change	12/02/09	Wednesday	56.82		14.0 (RES#7)	-4.00 (could not reach)
36		12/03/09	Thursday	59.09		15.0 (RES#7 modified)	-3.66	23 hours
37		12/04/09	Friday	61.36		20.0 (DIS#2)	-2.63					LHRS new angle (20 deg)	angle change could take one full shift
38		12/05/09	Saturday	63.64
39		12/06/09	Sunday	65.91
40		12/07/09	Monday	68.18
41		12/08/09	Tuesday	70.45
42		12/09/09	Wednesday	72.73
43		12/10/09	Thursday	75.00
44		12/11/09	Friday	77.27
45		12/12/09	Saturday	79.55
46		12/13/09	Sunday	81.82
47		12/14/09	Monday	84.09
48		12/15/09	Tuesday	86.36
49		12/16/09	Wednesday	88.64	6.068	20.0 (DIS#2)	-2.63		20 (DIS#2)	-2.63
50	Pass Change	12/17/09	Thursday	90.91	4.868	move both HRS to 12.9 deg			12.9 (RES#5)	-3.10	87 hours	left HRS angle survey and both spectrometer move to 12.9 deg.
51	Resonance Running	12/18/09	Friday	93.18	4.868	12.9 (RES#3)	-4.00	31 hours
52		12/19/09	Saturday	95.45	4.868	12.9 (RES#4)	-3.55	57 hours
53		12/20/09	Sunday	97.73	4.868
54		12/21/09	Monday	100.00	4.868							target warm up at the end of day, for endcap rate measurement?
55	beam stops at 7am	12/22/09	Tuesday		4.868
56	beam study	12/23/09	Wednesday
57	down	12/24/09