## Slide 1: HALLA G2P readiness review
Yves Roblin, CASA

## Slide 2: Beamline overview
bpms
harps
calorimeter
Fast raster
Notes: General schematic. The first blue box is the slow raster that was installed in the room left by the removal of EP. The local dump
Is shown as a red rectangle going to floor, in practice it does not. It is a number of tungsten plugs inserted in the front mouth of the
Septum magnet at the appropriate locations.
On the 1H04 girder (the inverted girder), the H04A quad is gone. Correctors are still there. There is a harp there.

## Slide 3: Initial commissioning

## Slide 4: Tasks breakdown for beamline comissioning
Task Description |  | duration(hours) | duration | lead
Matching at 1C05 | 0.33 | 6.0 | 0.25 | roblin/OOC
Initial Delivery to Hall A | 2.33 | 9.0 | 0.38 | roblin
BPM commissioning | 2.75 | 6.0 | 0.25 | musson
Silver Calorimeter | 3.75 | 4.0 | 0.17 | ahmad
Raster Size | 3.50 | 3.0 | 0.13 | roblin
FZ2 positioning(7 deg, 2.5T, main dump) | 4.33 | 8.0 | 0.33 | roblin
7 degrees,5.01T,main dump | 4.66 | 5.0 | 0.21 | roblin
90 degrees, 2.5T,local dump (-3.03 degrees) | 5.33 | 4.0 | 0.17 | roblin
90 degrees, 5.01 T, local dump (-6.078 degrees) | 5.50 | 4.0 | 0.17 | roblin
check match | 3.66 | 3.0 | 0.13 | roblin/OOC
check current interlocks for dipole | 5.66 | 1.0 | 0.04 | Roblin/OPS
Notes: Straight mode commissioning mostly done. What’s left to do is to calibrate bpm offsets relative to the harp.
Raster checks have to be done as well. We checked that rasters were working. Green means we did it already.

## Slide 5: Initial commissioning of line (12/14-12/22)
Beam commissioned in straight-thru.
Match to line done, beam spots on design.
Moller runs were done.
All diagnostics checked, problems identified and being corrected
CW of a few tens of nA delivered for physics detector checks.
Halla beam dump
Match into hall A
Notes: Adding thicker harp wires.
Lining up the 1H05 viewer
Beam is matched optimally, can be seen on dump with currents as low as 0.5 uamps, used to require 5 to 10 microamps. Will
make chicane commissioning much easier.

## Slide 6: Beam envelope and rastering
Slow raster to produce 2.2x2.2cm pattern
Fast raster to produce 3mmx3mm on top of it
Unrastered beam about 30 microns round at target
Beam about 50 microns round at Compton

## Slide 7: Expected Raster Ranges
Energy | X slow | Y slow | X fast | Y fast
1.1 GeV | +/- 2.1 kG cm | +/- 1.3 kG cm | +/- 0.15 kG cm | +/- 0.1 kG cm
2.2 GeV | +/- 4.2 kG cm | +/- 2.6 kG cm | +/- 0.30 kG cm | +/- 0.2 kG cm
3.3 GeV | +/- 6.3 kG cm | +/- 3.9 kG cm | +/- 0.45 kG cm | +/- 0.3 kG cm
Raster limits:
COIL | SLOW | FAST
X | 16.8 kG cm | 3.3 kG cm
Y | 16.8 kG cm | 3.3 kG cm
Notes: Fits in the range of the rasters. Can increase slow raster easily in order to relax fast raster a bit.
We used both rasters successfully during the first commissioning. We did not do a formal check at the target yet but did check
their functionality. The reason we did not do the formal check is that we had problems with the harps.

## Slide 8: Chicane commissioning
Notes: The chicane is designed to present the beam at the Hall A target with an angle such that it satisfies kinematics required for the
Physics setup. In most cases this is equivalent to setting up the chicane such that the main beam exits the target with zero outgoing angle and
go to the main dump. When not possible, we also can send it to a local dump.

## Slide 9: prerequisites
Beam line commissioned in straight-thru
BPM offsets (IPM1H05A/IPM1H05B) cross-calibrated with the harps (IHA1H01/IHA1H05A)
Rasters commissioned.
Notes: Already done
Just need the harps to work and then easy to do.
Follows from 1) and 2)
We will start with chicane in straight-thru to do these steps.

## Slide 10: Chicane calculations
Find setpoints such that elevation is zero at closing of chicane.
Incoming angle is compensated by field of target
Done via a spreadsheet. Results imported to Optim for full
Orbit.
Tracked into ELEGANT for multipole estimation
Checked with GEANT and full field map of target solenoid
Chicane design
Notes: The chicane is constrained by:
We want the beam to intersect target at beamline elevation
We want to present the beam with a specific angle (in many cases such that at the exit, there is no outgoing angle)
A spreadsheet was developed to interactively calculate the magnet setpoints and the FZ2 elevation.
During commissioning we can use that to find which adjustments are needed on magnets to lower/raise beam.

## Slide 11: Overview of physics runs
P | Target θ | Target B | Run # | Incoming θ | Tilting angle | Outgoing θ
1.159 | 90 | 2.5T | 1 | 11.94 | 5.97 | 0.0
1.159 | 7 | 2.5T | 2 | 1.437 | 0.7185 | 0.0
1.706 | 7 | 2.5T | 3 | 0.9763 | 0.4881 | 0.0
1.706 | 90 | 2.5T | 4 | 8.06 | 4.03 | 0.0
2.257 | 90 | 2.5T | 5 | 6.076 | 3.038 | 0.0
2.257 | 7 | 2.5T | 6 | 0.7381 | 0.369 | 0
2.257 | 90 | 5.01T | 7 | 6.079 | 0.0 | -6.079
2.257 | 7 | 5.01T | 8 | 1.4793 | 0.7396 | 0
3.355 | 90 | 5.01T | 9 | 4.086 | 0.0 | -4.086
3.355 | 7 | 5.01T | 10 | 0.9952 | 0.4976 | 0
Notes: Runs with non-zero outgoing angles, go to the local dump that is located in the entrance of the septum magnet. This dump is limited to 400 Watts. Not shown is the longitudinal polarization run which is essentially a straight-thru run with chicane magnets powered off.

## Slide 12: Beam trajectories
FZ1 fixed, FZ2 on vertical moving stand
FZ2
FZ1
Notes: FZ magnet type is a modified BZ magnet with a larger vacuum chamber (9.6 inches instead of 5.5) . FZ2 is on a vertical moving stand.
Only two runs are going to the local dump.
The rest is to the main dump. Precise values for the beam on local dump were determined by A. Gavalya by importing orbits into the CAD system.

## Slide 13: Magnet setpoints
# | E | Tgt | θin | Θout | B1(kG) | I1(A) | B2(kG) | I2(A)
1 | 1159.7625 | 90/2.5T | -8.98 | 11.94 | -3.02 | 168 | 7.02 | 394
2 | 1159.7625 | 7/2.5T | -1.08 | 1.44 | -0.36 | 18 | 0.85 | 46
3 | 1706.7625 | 7/2.5T | -0.73 | 0.98 | -0.36 | 18 | 0.85 | 46
4 | 1706.7625 | 90/2.5T | -6.04 | 8.06 | -3.00 | 168 | 6.99 | 394
5 | 2257.7625 | 90/2.5T | -4.55 | 6.08 | -2.99 | 168 | 6.98 | 394
6 | 2257.7625 | 7/2.5T | -0.55 | 0.74 | -0.36 | 18 | 0.85 | 46
7 | 2257.7625 | 90/5.01T | -4.49 | 6.08 | -2.94 | 164 | 6.93 | 388
8 | 2257.7625 | 7/5.01T | -1.11 | 1.48 | -0.73 | 39 | 1.70 | 94
9 | 3357.7625 | 90/5.01T | -3.02 | 4.09 | -2.94 | 164 | 6.93 | 388
10 | 3357.7625 | 7/5.01T | -0.74 | 0.99 | -0.73 | 39 | 1.70 | 94
Notes: Why is field same for runs of different energies?
Answer:
What is constrained is the elevation and angle at target. One knob is the deflection at first magnet, (second magnet is constrained )
And other knob is elevation of second.
Turns out that as long as we are compensating for same target field (combination of field and angle of solenoid),we end up with same constraints and fields
since deflections scales with energy.
Exact fields will be adjusted during commissioning in order to get beam on target at correct location.
Notice that as a consequence, we only have to commission a few configurations. Changing energy simply will mean scaling the quads and correctors.
The main dipoles will stay the same.
Currents were calculated using field maps obtained by measurements carried out by K. Baggett.

## Slide 14: Procedure
Load magnet setpoints for quads and dipoles
Establish tune beam to 1H01 viewer with zero incoming angle
Insert 1H05 viewer and adjust MFZ1H05A dipole to center beam in it.
Retract viewer, adjust MFZ1H05B such that bpms IPM1H05A and IPM1H05B both read zero.
Go CW and raise current until seen on dump viewer (0.5 microamps)
Check that beam is centered vertically on viewer. If not, adjust MFZ1H05B until it is.
Go back to tune mode.
Slowly increase slow raster and use Spot++ to assess beam size.
Notes: Detailed ATLIS will be given for OPS to follow. I will be in the control room to oversee initial tuning.

## Slide 15: Machine protection
Notes: The chicane is designed to present the beam at the Hall A target with an angle such that it satisfies kinematics required for the
Physics setup. In most cases this is equivalent to setting up the chicane such that the main beam exits the target with zero outgoing angle and
go to the main dump. When not possible, we also can send it to a local dump.

## Slide 16: Interlock systems
Beam current limited to :
  2 μamps CW if going to hall A dump
  150 nA CW if going to local dump
Done via Beam Loss Accounting (BLA) system current limits (hardware limits with comparator on a current cavity)

## Slide 17: Interlock Systems (cont)
FZ1 and FZ2 dipole magnet fields
A comparator with a window of +/- 5 % or better will be set around the FZ1 and FZ2 setpoint. It will be tied to the Fast shutdown system (FSD).

## Slide 18: Interlock Systems (cont)
Local dump integrity
Temperature measurement probes will be installed on the local dump and monitored for abnormal heating. Will be tied to the FSD system to terminate beam if temperature goes above a predetermined threshold.

## Slide 19: Interlock Systems (cont)
Hall A Septum
Beam Loss Monitors (BLM) probes will be placed downstream of the target area to monitor for scraping in the vicinity of the Septum. Will be tied to pull a FSD.

## Slide 20: Interlock Systems (cont)
Hall A Target magnet
The magnet field will be set at the desired value and a FSD will be pulled if it drops during data taking.

## Slide 21: Interlock Systems (cont)
Hall A dump
Standard procedure for this dump. The BLM probes placed on either side (left and right) will be tied to the FSD.
Maximum power limit is 400 Watts driven by the need to protect the target windows not the dump..
Notes: Target windows are aluminum.

## Slide 22: Extra slides

## Slide 23: Position on local dump
Actual design will be presented in R. Wines talk.
3.3/90/5.01T
2.2/90/5.01T
1.1/90/5.01T
Notes: This is a schematic. More details in R. Wines talk. Red spots is the beam for the 3 different runs going to the local dump.
All parts of the dump are made of tungsten. The 1.159 GeV/c /90 degrees/5.01T run is not listed in the physics run on slide 11 but is
Being considered for optics calibration and may be used.