## Slide 1
Introduction / Overview
Jian-ping Chen
g2p /GEp Readiness Review
1/17/2012

## Slide 2
Charge
Experimental Goals/Requirements
Experimental Setup
Polarized Target
Beamline
Support Structure / Beam Dump / Field
Spectrometers / Detectors / DAQ
Safety Considerations
December Commissioning
Preparation Status / Installation
Commissioning
Experimental Run Plan
Documents
Outline

## Slide 3
E08-027 : Proton g2 Structure Function
Fundamental spin observable has never been measured at low or moderate Q2
BC Sum Rule : violation suggested for proton at large Q2, but found satisfied for the neutron & 3He.
Spin Polarizability : Major failure (>8 of PT for neutron LT. Need g2 isospin separation to solve.
Hydrogen HyperFine Splitting : Lack of knowledge of g2 at low Q2 is one of the leading uncertainties.
Proton Charge Radius : also one of the leading uncertainties in extraction of <Rp> from H Lamb shift.
A- rating by PAC33
BC Sum Rule
A. Camsonne, J. P. Chen, D. Crabb, K. Slifer*
g2 data strongly anticipated by theorists
Spin Polarizability LT

## Slide 4
E08-007: Form Factor Ratio GE/GM
Measure asym in both HRS simultaneously and form the super-ratio:
Resolve/refute possible structure in the FF at low Q2 (Freidrich and Walcher, 2003)
Precise knowledge of the FFs at low Q2 is critical for:
  GPDs in DVCS
  Strange FF from Parity Violation
Provide definitive measurement of the Proton Zemach Radius and measurement of the charge radius.
Projected Uncertainties
G. Ron*, D. Higintbothan, R. Gilman, J. Arrington, A. Sarty, D. Day

## Slide 5
Goal (g2p experiment) : measure g2p with a precision ~ 5-7%
by measuring transversely polarized cross section difference = A x 
Measure both asymmetries and cross sections to ~4-5%
Control total systematics to 3-5%,
(each sub-system to 1-3%)
Goal (GEp): measure GEp with a precision to ~<1%
by measuring asymmetry ratio between left HRS and right HRS
 Main systematics: target spin direction (0.1 degree in , 2 mr in _e)
difference between L / R
Need good optics: HRS+septum+target field
Experimental Goals/Requirements

## Slide 6
REGION 1
REGION 2
REGION 3
REG 4
REGION 5
Slow Raster
FZ1
FixedStand
FZ2 Telescoping Stand
DUMP
TARGET
Polarized Solid NH3 Target
Target material irradiation
Beamline
Magnetic Chicane/Beamline modifications.
Low beam current BCM/BPMs, Slow Raster
Hall A Engineering/Design
Local Beam Dump
Septum Magnets
Hall Infra-structure/Chamber/ Target/magnet mount
Spectrometer/Detectors/QAD/Optics
Polarimetry/3rd arm
BPMs
Hall C target magnet failed
 Using Hall B magnet
Dec. commissioning (beamline/det)
successful
commissioned most components
identified a few problems
Experimental Setup
Septa/HRS
Harps
Notes: J:/jlab work/HALL A/g2P

## Slide 7
Target magnet failure
 use Hall B magnet
 delay of experiment (Mid-Feb)
 no time for setpa-out runs
Commissioning in December with a 12C foil target
 Beamline components mostly commissioned
BPM(SEE), BCM, Tungsten Calorimeter, Slow Raster, Moller, Viewer, PSS…
 Found problems: being addressed
1) exit beam pipe (mis-alignment due to vacuum force)
2) superharp
 HRS/Septum/detectors/DAQ/3rd arm commissioned
optics: partially started
Not commissioned: 4Ch BPM readout (not ready in Dec)
Polarized target, Chicane, Local dump
Main part optics (need sieve and target field)
Main Events

## Slide 8
3.4 GeV, 12.5 deg (5T)
2.3 GeV, 12.5 deg (5T)
3.4 GeV, 6 deg (5T)
2.3 GeV, 6 deg (5T, 2.5T)
1.7 GeV, 6 deg (2.5T)
1.2 GeV, 6 deg (2.5T)
Lower target field from 5T to 2.5T
for three lowest energy settings
Kinematic Settings
Two configurations: with septa (6 degree) (target at 87 cm upstream)
and without septa (12.5 degrees) (target at original pivot)
G2p : target at 90 degrees for all and 0 degree for 3.4 GeV
GEp : target at 20 degree  7 degrees

## Slide 9
Target Progress (C. Keith and target team)
  Hall B magnet adapted to the target
  Ready for installation
  Target material irriadiation at NIST: did once, 2nd next week
  Cold-down tests twice at UVa, polarization @ 2.5T ~25%
Progress with Beam Line System (T. Michalski and beamline team)
  Design completed, all components installed/tested
  Most components commissioned
  4-ch new BPM readout, work remaining (software)
  Superharp: has a solution
  Beam exit pipe (vacuum force): being worked on
  Chicane; to be commissioned
Progress in Hall A (R. Wines/E. Folts/A team, Slifer/g2p team)
  Platform/structure ready
  Septum/HRS/detectors/DAQ commissioned
  3rd arm commissioned
  Moller commissioned
  Initial optics
  Local dump
Overview of Progress

## Slide 10
Target installation/testing: now to mid-Feb (2/15)
Commissioning during or after target tests complete
Commissioning beamline/chicane/localdump/target/optics
Running from mid Feb to mid May
enough beam time at 2.2 and 3.4 GeV,
but tight at 1.1 and 1.7 GeV due to constraints
from running together with Hall C and Hall B
Commissioning and Run Plan

## Slide 11
Target safety: (Chris)
Following all safety considerations as in SANE
Additional controls in the target area (Ed/Chris)
Beamline safety:
PSS system to include new changes (Chicane/target/dump) (Tim/Yves)
Ion chambers, viewers, thermal couples (dump)
Radiation consideration: (Pavel/George)
LC dump design (Al worked with Pavel)
RADCON group calculations of radiation levels (George)
Safety documents: (All)
RSAD (draft) ready (pavel)
Radiation effects (George)
ESAD (draft ready)
OSPs: mostly ready
Safety Considerations and Documents