## tasks
| APEX Tasks | Contact | Status and questions
1 | Target drawings complete, dwgs need sign off & submit to DCG | Joyce | done
2 | Target, purchase target ladder & remaining assembly parts | Silviu | ?
3 | Target, motion & motion control- assembly & test | Silviu, Jack | ?
4 | Scattering chamber, check which chamber is correct for target | Joyce | confirmed using same chamber that is in Hall now for Tritium
5 | Scattering chamber, assemble target & target in chamber | Jessie, Silviu | ?
6 | Scattering chamber, check o-ring seal requirement on top, **order bellows & o-ring early | Silviu | ?
7 | Extension box, install scifi & test | Bogdan, Jessie | Extension box is in the Hall, scifi is not installed yet. Bogdan plans to start installation of scifi in extension box in mid to late November. Has a vacuum/leak check been done of extension box ?
8 | Extension box, controls & motion for scifi | Bogdan, Jack | ". Where is sieve slit ?
9 | Extension box, get & connect cables | Bogdan | "
10 | Power Supplies for correctors, send Jack corrector requirements | Robin | sent
11 | Power Supplies for correctors & septum, connect | Jack, Jessie | Received corrector requirements, need septum requirements confirmed
12 | Septum, modify bussbars & test magnet | Jessie, Jack | ?
13 | LCW, verify cooling of magnest, add pump if needed | Jack, Jessie, Whit | ?
14 | Documentation, send Thia document, justification for ERR changes | Bogdan | done
15 | Assembly, test fit chamber to extension box to vacuum chambers to septum to HRS, as feasible | Jessie | ?
16 | Assembly, define alignment requirements, verify assembly/alignment procedure | Jessie | Need to contact Survey to initiate alignment request (need 0.5 to 1.0 mm placement for beamline, then septum & correctors ok) ?
17 | Vacuum chambers, complete |  | done
18 | Septum support, complete design, procure | Alan, Robin | new install fixture and weldment delivered. Box assembly to be delivered by Oct 5.
19 | Correctors, procure | Robin | delivered
20 | extension box support, procure | Robin | delivered
21 | Septum, procure & replace support feet | Robin, Jessie | Jlab machine shop to deliver by Nov 2
22 | Contact Radcon to verify shielding and beam dump | Bogdan | ?
23 | Need to contact AccOps- position of beamline corrector, control of Apex correctors, location of radiation protection chamber | Jessie, Jack | Contact Ives ?