## Sheet1
HALL C A1N D2N EXPERIMENT (BUILD COMPLETION STATUS) |  | MATERIAL IN HOUSE | ORDER MATERIAL REQ'D | WORK REQUIRED | BUILD ASSIGNED WALTER KELLNER | BUILD ASSIGNED BERT METZGER | BUILD ASSIGNED JP CHEN | BUILD ASSIGNED MACHINE SHOP | BUILD ASSIGNED TARGET GROUP
NUMBER | NAME |  |  |  | PERCENT COMPLETE STATUS
SHORTCUT LINK TO UPDATED DRAWINGS
67507-00001 | PLATFORM ASSEMBLY |  | FASTENERS | HALL ASSEMBLE | 70
67507-00002 | LOWER DECK WELDMENT | Y |  | CUT, WELD | 100
67507-00003 | ADAPTER SPOOL |  |  |  | 100
67507-00004 | SHORT DECK SUB-ASSEMBLY | Y |  | CUT, WELD | 100
67507-00005 | LONG DECK SUB-ASSEMBLY | Y |  | CUT, WELD | 100
67507-00006 | PLAFFORM STAIRS | Y | FASTENERS | MACH, CUT, WELD | 70
67507-00007 | HALL C 3He LOWER DECK ASSEMBLY | Y | FASTENERS, HAND RAILS | HALL ASSEMBLE | 20
67507-00008 | SHORT DECK SUPPORT LEGS | Y |  | CUT, WELD, MACH. |  |  |  | 0 (June 1)
67507-00009 | PLATFORM SUPPORT STRUCTURE |  | FASTENERS |  | 100
67507-00010 | HALL C He3 LASER BOX SUPPORT STRUCTURE | Y | FASTENERS | MODIFY EXISTING | 70
67507-00011 | PLATFORM FILLER PLATES |  |  |  | 100
67507-00012 | LOWER DECK BEAMLINE ADAPTER | Y |  | CUT, WELD, MACH. | 100
67507-00013 | TRANSITION BEAM PIPE |  |  | MACH, CUT, WELD | 80
67507-00014 | Be_WINDOW ENTRANCE EXIT BEAMPIPE ASSY |  |  | VACUUM TEST |  | 100 |  |  | 100
67507-00015 | SMALL BEAMPIPE WELDMENT |  |  | CUT, WELD | 100
67507-00016 | 2 3/8 BEAMPIPE CLAMP LOWER AND UPPER | [6 empty] | 100
67507-00017 | SUPERHARP GIRDER MODIFICATION |  | ALL | DESIGN, BUILD |  | 100
67507-00018 | FILLER PLATE AND HANDRAIL ASSEMBLY | Y | FASTENERS, HAND RAILS | CUT, HALL ASSEMBLE | 0
67507-00019 | UPPER PLATFORM HANDRAIL AND SINGLE STEP ASSEMBLY | Y | HAND RAILS | CUT, HALL ASSEMBLE | 100
67507-00020 | 2 3/8 BEAMPIPE SUPPORT ASSY | [6 empty] | 100
67507-00021 | TARGET ADAPTER PLATE | Y |  | MACHINE | 100
67507-00022 | Be WINDOW BEAMPIPE WELDMENT |  |  |  |  | 100
67507-00023 | Be 2 3/4 WINDOW FLANGE |  |  |  |  | 100
67507-00024 | Be 2 3/4 WINDOW FOIL CLAMP | Y |  | MACHINE | 100
67507-00025 | He3 COLLIMATOR BEAMPIPE |  |  | BUILD |  |  |  | 100
67507-00032 | EPR PORT TUBE |  |  |  |  | 100
67507-00034 | EPR ASSEMBLY | [5 empty] | 100
67507-00035 | MIRROR ADJ PLATE |  |  |  |  | 100 |  | 100
67507-00036 | MIRROR ASSY | [5 empty] | 100
67507-00037 | LADDER PLATE MODIFICATION | [6 empty] | 100
67507-00038 | OVEN TOP PLATE |  |  |  |  | 100
67507-00039 | OVEN WALLS |  |  |  |  | 100
67507-00040 | OVEN LASER BEAM STOP |  |  |  |  | 100
67507-00041 | OVEN SEAL PLATE |  |  |  |  | 100
67507-00042 | OVEN BOTTOM AND RETAINER PLATE |  |  |  |  | 100
67507-00043 | OVEN ITEMS |  |  |  |  | 100
67507-00044 | CS85 OVEN ASSEMBLY |  |  |  |  | 100
67507-00045 | OVEN SEAL |  |  |  |  | 100
67507-00046 | THREADED KNOB WITH STUD |  |  |  |  | 100
67507-00047 | TARGET LADDER ASSY |  | FASTENERS | ASSEMBLE |  |  | 0
67507-00048 | PICKUP COIL MOUNT | [5 empty] | 100
67507-00049 | PICKUP COIL ASSEMBLY | [5 empty] | 100
67507-00050 | OVEN ASSEMBLY | [5 empty] | 100
67507-00051 | OVEN / TARGET LADDER ASSEMBLY |  |  | HALL ASSEMBLE |  |  | 0
67507-00052 | SUPPORT BRACKET MOUNT MODIFICATION |  |  |  | 100
67507-00053 | A1N STATIC ASSY |  |  | MODIFY |  |  |  | 100
67507-00054 | LIMIT SWITCH MTG PL MODIFICATION |  |  | MODIFY |  |  |  | 100
67507-00055 | MAIN SUPPORT ITEMS | Y |  | CUT, WELD, MACH. |  |  |  | 50 (June 1)
67507-00056 | REFERENCE CELL CONN SUPPORT | [6 empty] | 100
67507-00057 | REFERENCE CELL ASSEMBLY |  |  | ASSEMBLE |  |  | 0
67507-00058 | CARTRIDGE MOUNT PLATE |  |  |  | 100
67507-00059 | MOUNTING PLATE FOR PU-COLIM-DUMP MODIFICATION |  |  |  | 100
67507-00060 | MAIN SUPPORT ASSEMBLY | Y | [5 empty] | 100
67507-00061 | COIL SUPPORT BRKT MODIFICATION |  |  | MACHINE | 100
67507-00062 | 54.75 MAG COIL MT SUBASSY MODIFICATION |  |  |  | 100
67507-00063 | SMALL PLATFORM (JL0040090) | Y |  | BUILD |  |  |  | 100
67507-00064 | SMALL MIRROR MOUNT ANGLE | Y | [5 empty] | 100
67507-00065 | LASER ENCLOSURE SAFETY PLATES | Y |  | MACHINE |  |  |  | 100
67507-00066 | LASER ENCLOSURE SMALL ASSY |  |  | ASSEMBLE | 0
67507-00067 | BREADBOARD 3 WITH OPTICS ASSY | Y |  | ASSEMBLE, MACH. | 100 |  | 0
67507-00068 | TOP PLATE ENCL 4 - 1/16 THK ASSY | Y | FASTENERS | MODIFY, MACH. | 0
67507-00069 | END PANEL ENCL 4 - 1/16 THK ASSY | Y | FASTENERS | MODIFY, MACH. | 0
67507-00070 | SIDE PANEL ENCL 4 W/ HOLE ASSY | Y | FASTENERS | MODIFY, MACH. | 0
67507-00071 | TOP SML COIL SUPP MODIFICATION | [6 empty] | 100
67507-00072 | RF MOUNT ASSY |  |  | MACH. ASSEMBLE | 100
67507-00073 | PU COIL-COLIM-ASSY |  |  | MACH. ASSEMBLE | 100
67507-00074 | WORKING CELL GLUE FIXTURE ASSEMBLY | [6 empty] | 100
67507-00075 | WORKING CELL AND BOTTOM PLATE GLUE ASSY | [6 empty] | 100
67507-00076 | BOTTOM RF SUPPORT PLATES |  |  |  | 100
67507-00077 | LEADSCREW HANDWHEEL ASSY | [6 empty] | 100
67507-00078 | CORRECTOR COIL ASSEMBLY | Y | FASTENERS | MACHINE | 80
67507-00079 | CORRECTOR COIL INSTALLATION |  |  | HALL ASSEMBLE | 0
67507-00080 | TARGET SYSTEM ASSEMBLY |  |  | HALL ASSEMBLE | 5
67507-00081 | SUPPORT BRACKET MOUNT ADAPTER |  |  |  | 100
67507-00082 | EXPERIMENT INSTALLATION ASSEMBLY _(HIGHEST LEVEL ASSY) |  |  | HALL ASSEMBLE | 0
67507-00083 | ELECTRONIC SHIELDING INSTALLATION ASSEMBLY |  |  |  | 0
67507-00084 | UNDER DECK SHIELD HOUSE ASSEMBLY | SOME | MODIFIED SOS PANEL | MACH. ASSEMBLE | 10
67507-00085 | CABLE RUN INSTALLATION | SOME | CABLE TRAYS |  | 0
67507-00086 | HELMHOLTZ COIL COVERS |  | BLACK LEXAN was G10 | CUT OUT, FIT | 0
67507-00087 | CARBON TARGET ITEMS |  | CARBON FOIL | MACHINE |  |  |  |  | 100
67507-00088 | NMR-EPR SHIELD HOUSE ASSEMBLY |  | ALUMINUM AND HARDWARE | MACH. ASSEMBLE |  |  |  | 0 (Items)
67507-00089 | BeO TARGET AND MOUNTING ITEMS |  | BeO MATERIAL | MACHINE |  | 100 (BeO) |  | 100 (Items)
67507-00090 | LIMIT SWITCH PLATE SHORT | Y |  | MACHINE |  |  |  | 100
67507-00091 | REFERENCE CELL A1N D2N |  |  | BUILD |  |  | 0
67507-00092 | FLOOR LOCATIONS FOR SURVEY |  |  | NONE | 100
67507-00093 | EPR LARGE ANGLE PLATE |  |  |  |  | 100
67507-00094 | EPR FIBER HOLDER |  |  |  |  | 100
67507-00095 | EPR FIBER HOLDER LIGHT SHIELD |  |  |  |  | 100
67507-00096 | EPR FIBER HOLDER WASHER |  |  |  |  | 100
67507-00097 | FIBER HOLDER ATTACHMENT TUBE |  |  |  |  | 100
67232-00001 | HMS Q1 VAC 27.25L ASSEMBLY | Y | FASTENERS | MACHINE CLAMPS | 80
67507-00098 | ADJUSTER BEAMPIPE ASSEMBLY |  |  | VACUUM TEST |  | 95
67507-00099 | HORIZONTAL COMPASS MODIFICATION |  | UK BUILDING |  |  | 0
67507-00100 | HORIZONTAL COMPASS MOUNT FIXTURE |  | UK BUILDING |  |  | 0
67507-00101 | HORIZONTAL COMPASS INSTALLATION ASSEMBLY |  | UK BUILDING |  |  | 0
67507-00102 | PNMR COIL MOUNT HALF 3He Cell |  |  |  |  | 100
67507-00103 | EPR EXTRA COIL ASSY |  |  |  |  | 100 (July 1)
| DRIVE MOTOR CONTROLLER ordered |  | MOTOR ( HALL A) |  |  | 100 (July 1)