## Sheet1
Activity ID | Activity Name | Resource Name | Resource Type | Start | Finish | Budgeted Units | Actual start | Actual Done
Q2-00005 | Move SHMS to Beam Right | Hall C Tech | Labor | 2016-09-30 | 2016-10-03 | 1
Q2-00025 | Alignment fiducials | Alignment Tech | Labor | 2016-10-06 | 2016-10-06 | 3
Q2-00030 | Lift magnet onto SHMS | Hall C Techs | Labor | 2016-10-06 | 2016-10-07 | 1 | 2016-10-07 | 2016-10-07
Q2-00020 | Electrical Tests | Hall C Engineer | Labor | 2016-10-06 | 2016-10-06 | 0.5 | 2016-10-06 | 2016-10-06
Q2-00030 | Lift magnet onto SHMS | Hall C Tech | Labor | 2016-10-06 | 2016-10-07 | 3 | 2016-10-07 | 2016-10-07
Q2-00015 | Weld Fiducial Sockets | Hall C Tech | Labor | 2016-10-06 | 2016-10-06 | 0.5 | 2016-10-07 | 2016-10-07
Q2-00015 | Weld Fiducial Sockets | Hall C Welder | Labor | 2016-10-06 | 2016-10-06 | 0.5 | 2016-10-07 | 2016-10-07
Q2-00035 | Remove transport pins | Hall C Tech | Labor | 2016-10-07 | 2016-10-07 | 1.5 | 2016-10-07 | 2016-10-07
Q2-00040 | Assemble Yoke | Hall C Tech | Labor | 2016-10-10 | 2016-10-12 | 6 | 2016-10-10 | 2016-10-12
Q2-00065 | Install vacuum flanges and pumps | Hall C Tech | Labor | 2016-10-10 | 2016-10-10 | 1 | 2016-10-07 | 2016-10-07
Q2-00085 | Magnet pump down | Hall C Tech | Labor | 2016-10-10 | 2016-10-15 | 1 | 2016-10-07 | 2016-10-13
Q2-00045 | Assemble magnet access platform | Hall C Tech | Labor | 2016-10-12 | 2016-10-17 | 9 | 2016-10-13
Dipole-00015 | Magnet ERR Response to Recomendations | Hall C Engineer | Labor | 2016-10-13 | 2016-10-19 | 5 | 2016-10-13
Q2-00147 | Install AC Power for top of CCR | ELEC TECH ELECTRICIAN | Labor | 2016-10-17 | 2016-10-19 | 4
Q2-00090 | Leak test and pressure test | Hall C Engineer | Labor | 2016-10-17 | 2016-10-17 | 1
Q2-00090 | Leak test and pressure test | Hall C Tech | Labor | 2016-10-17 | 2016-10-17 | 1
Q2-00070 | Install relief valve tree | Hall C Tech | Labor | 2016-10-17 | 2016-10-18 | 2
Q2-00095 | N2 gas purge magnet helium circuit | Hall C Tech | Labor | 2016-10-18 | 2016-10-20 | 3 | 2016-10-14
Q2-00075 | Install CCR Top Hardware | Hall C Tech | Labor | 2016-10-18 | 2016-10-20 | 2 | 2016-10-13
Q2-00050 | Dress I&C Feedthrus | Spec Support Group | Labor | 2016-10-18 | 2016-10-20 | 2 | 2016-10-17
Q2-00060 | Check out I&C | Hall C Engineer | Labor | 2016-10-20 | 2016-10-26 | 4
Q2-00080 | Calibrate JT Valves | Hall C Engineer | Labor | 2016-10-20 | 2016-10-24 | 1
Q2-00055 | Connect I&C cables | Hall C Tech | Labor | 2016-10-20 | 2016-10-26 | 4
Q2-00080 | Calibrate JT Valves | Hall C Tech | Labor | 2016-10-20 | 2016-10-24 | 2
Q2-00100 | Connect DC water cooled Bus | Hall C Tech | Labor | 2016-10-26 | 2016-10-27 | 2
Q2-00100 | Connect DC water cooled Bus | Spec Support Group | Labor | 2016-10-26 | 2016-10-27 | 1
Q2-00105 | Connect N2 gas vent line, warm He return line | Hall C Tech | Labor | 2016-10-27 | 2016-10-28 | 2
Q2-00110 | Install Lead gas return lines | Hall C Tech | Labor | 2016-10-28 | 2016-11-02 | 6
Q2-00115 | Leak test Helium gas lines and lead return line | Hall C Tech | Labor | 2016-11-02 | 2016-11-03 | 1
Q2-00120 | Pump and purge helium circuit | Hall C Tech | Labor | 2016-11-03 | 2016-11-07 | 2
Dipole-00020 | Transport into Hall C | Lockwood | Nonlabor | 2016-11-03 | 2016-11-03 | 1
Dipole-00030 | Electrical Tests | Hall C Engineer | Labor | 2016-11-04 | 2016-11-04 | 0.5
Dipole-00025 | Weld Fiducial Sockets | Hall C Welder | Labor | 2016-11-04 | 2016-11-04 | 0.5
Dipole-00035 | Alignment fiducials | Alignment Tech | Labor | 2016-11-07 | 2016-11-07 | 2
Q2-00125 | Circulate warm He gas thru magnet | ESR operator | Labor | 2016-11-07 | 2016-11-09 | 0.4
Q2-00125 | Circulate warm He gas thru magnet | Hall C Tech | Labor | 2016-11-07 | 2016-11-09 | 2
Dipole-00040 | Lift magnet onto SHMS | Hall C Tech | Labor | 2016-11-08 | 2016-11-08 | 3
Dipole-00040 | Lift magnet onto SHMS | Lockwood | Nonlabor | 2016-11-08 | 2016-11-08 | 1
Q2-00135 | Insert U-tubes | ESR operator | Labor | 2016-11-09 | 2016-11-10 | 1
Dipole-00045 | Assemble Yoke | Hall C Tech | Labor | 2016-11-09 | 2016-11-10 | 6
Q2-00135 | Insert U-tubes | Hall C Tech | Labor | 2016-11-09 | 2016-11-10 | 2
Q2-00142 | Final Alignment | Alignment Tech | Labor | 2016-11-10 | 2016-11-15 | 6
Q2-00140 | Cool down to 80 K | Hall C Engineer | Labor | 2016-11-10 | 2016-11-20 | 1
Q2-00142 | Final Alignment | Hall C Tech | Labor | 2016-11-10 | 2016-11-15 | 6
Dipole-00050 | Rotate to 9.2 degrees | Hall C Tech | Labor | 2016-11-11 | 2016-11-11 | 3
Dipole-00055 | Assemble magnet access platform | Hall C Tech | Labor | 2016-11-14 | 2016-11-16 | 9
Dipole-00075 | Remove transport pins | Hall C Tech | Labor | 2016-11-14 | 2016-11-14 | 1.5
Dipole-00080 | Install vacuum flanges and pumps | Hall C Tech | Labor | 2016-11-14 | 2016-11-14 | 1
Q2-00143 | Initial Quench Detector Settings | Hall C Engineer | Labor | 2016-11-15 | 2016-11-16 | 1
Q2-00130 | Install Q1-Q2 vacuum tube | Hall C Tech | Labor | 2016-11-15 | 2016-11-17 | 4
Dipole-00085 | Install relief valve tree | Hall C Tech | Labor | 2016-11-15 | 2016-11-15 | 2
Q2-00144 | Install Electrical Shields on top of CCR | Hall C Tech | Labor | 2016-11-15 | 2016-11-17 | 1
Dipole-00090 | Install CCR Top Hardware | Hall C Tech | Labor | 2016-11-16 | 2016-11-17 | 2
Dipole-00100 | Splice Prep work | Hall C Tech | Labor | 2016-11-16 | 2016-11-21 | 5
Dipole-00100 | Splice Prep work | SigmaPhi | Nonlabor | 2016-11-16 | 2016-11-21 | 5
Dipole-00060 | Assemble shield house - around Dipole | Hall C Tech | Labor | 2016-11-17 | 2016-11-17 | 3
Dipole-00095 | Calibrate JT Valves | Hall C Engineer | Labor | 2016-11-18 | 2016-11-21 | 1
Dipole-00065 | Install CCR and stand | Hall C Tech | Labor | 2016-11-18 | 2016-11-18 | 3
Beam-00005 | Install Drift Chambers | Hall C Tech | Labor | 2016-11-18 | 2016-11-28 | 2
Dipole-00095 | Calibrate JT Valves | Hall C Tech | Labor | 2016-11-18 | 2016-11-21 | 2
Beam-00005 | Install Drift Chambers | Hall C Visiting User | Labor | 2016-11-18 | 2016-11-28 | 2
Q2-00145 | Helium fill | ESR operator | Labor | 2016-11-21 | 2016-11-22 | 0.4
Dipole-00070 | Install Vapor cooled leads | Hall C Engineer | Labor | 2016-11-21 | 2016-11-21 | 0.25
Q2-00145 | Helium fill | Hall C Engineer | Labor | 2016-11-21 | 2016-11-22 | 1
Q2-00150 | Adjust controls | Hall C Engineer | Labor | 2016-11-21 | 2016-11-22 | 1
Dipole-00070 | Install Vapor cooled leads | Hall C Tech | Labor | 2016-11-21 | 2016-11-21 | 0.5
Dipole-00105 | Splice SC | Hall C Tech | Labor | 2016-11-21 | 2016-11-26 | 5
Q2-00150 | Adjust controls | Hall C Tech | Labor | 2016-11-21 | 2016-11-22 | 2
Dipole-00105 | Splice SC | SigmaPhi | Nonlabor | 2016-11-21 | 2016-11-26 | 5
Q2-00155 | Low power testing ~ 10 % | Hall C Engineer | Labor | 2016-11-23 | 2016-11-28 | 4
Q2-00155 | Low power testing ~ 10 % | Hall C Tech | Labor | 2016-11-23 | 2016-11-28 | 2
Q2-00155 | Low power testing ~ 10 % | SigmaPhi | Nonlabor | 2016-11-23 | 2016-11-28 | 2
Dipole-00110 | Insulate SC leads and test | Hall C Tech | Labor | 2016-11-28 | 2016-11-28 | 1
Dipole-00110 | Insulate SC leads and test | SigmaPhi | Nonlabor | 2016-11-28 | 2016-11-28 | 1
Q2-00160 | Progressive testing and support adjustment | Hall C Engineer | Labor | 2016-11-29 | 2016-12-12 | 20
Dipole-00115 | install internal I&C wires | Hall C Tech | Labor | 2016-11-29 | 2016-11-29 | 1
Q2-00160 | Progressive testing and support adjustment | Hall C Tech | Labor | 2016-11-29 | 2016-12-12 | 10
Dipole-00115 | install internal I&C wires | SigmaPhi | Nonlabor | 2016-11-29 | 2016-11-29 | 1
Q2-00160 | Progressive testing and support adjustment | SigmaPhi | Nonlabor | 2016-11-29 | 2016-12-12 | 10
Dipole-00120 | Dress I&C feedthrus | Spec Support Group | Labor | 2016-11-29 | 2016-12-05 | 5
Dipole-00125 | weld He tubes | Hall C Tech | Labor | 2016-11-30 | 2016-12-02 | 3
Dipole-00125 | weld He tubes | Hall C Welder | Labor | 2016-11-30 | 2016-12-02 | 3
Q3-00005 | Transport into Hall C | Lockwood | Nonlabor | 2016-12-01 | 2016-12-01 | 1
Q3-00015 | Electrical Tests | Hall C Engineer | Labor | 2016-12-02 | 2016-12-02 | 0.5
Q3-00010 | Weld Fiducial Sockets | Hall C Tech | Labor | 2016-12-02 | 2016-12-02 | 0.5
Q3-00010 | Weld Fiducial Sockets | Hall C Welder | Labor | 2016-12-02 | 2016-12-02 | 0.5
Q3-00020 | Alignment fiducials | Alignment Tech | Labor | 2016-12-05 | 2016-12-05 | 2
Dipole-00130 | Pump down and Leak test He Circuit | Hall C Tech | Labor | 2016-12-05 | 2016-12-09 | 5
Dipole-00170 | Check out I&C | Hall C Engineer | Labor | 2016-12-06 | 2016-12-09 | 4
Dipole-00165 | Connect I&C cables | Hall C Tech | Labor | 2016-12-06 | 2016-12-09 | 4
Q3-00025 | Lift magnet onto SHMS | Hall C Tech | Labor | 2016-12-06 | 2016-12-06 | 3
Q3-00035 | Remove transport pins | Hall C Tech | Labor | 2016-12-07 | 2016-12-07 | 1.5
Q3-00065 | Install vacuum flanges and pumps | Hall C Tech | Labor | 2016-12-07 | 2016-12-07 | 1
Q3-00030 | Rotate SHMS to Beam Left | Hall C Tech | Labor | 2016-12-07 | 2016-12-07 | 1
Q3-00040 | Assemble Yoke | Hall C Tech | Labor | 2016-12-08 | 2016-12-09 | 6
Dipole-00180 | Connect DC water cooled Bus | Hall C Tech | Labor | 2016-12-12 | 2016-12-12 | 2
Q3-00045 | Assemble magnet access platform | Hall C Tech | Labor | 2016-12-12 | 2016-12-14 | 9
Dipole-00135 | Weld N2 tubes | Hall C Tech | Labor | 2016-12-12 | 2016-12-12 | 1
Dipole-00135 | Weld N2 tubes | Hall C Welder | Labor | 2016-12-12 | 2016-12-12 | 1
Dipole-00180 | Connect DC water cooled Bus | Spec Support Group | Labor | 2016-12-12 | 2016-12-12 | 1
Q3-00090 | Leak test and pressure test | Hall C Engineer | Labor | 2016-12-13 | 2016-12-13 | 1
Q2-00165 | Acceptance Test | Hall C Engineer | Labor | 2016-12-13 | 2017-01-04 | 20
Dipole-00140 | Pump down and Leak test LN2 Circuit | Hall C Tech | Labor | 2016-12-13 | 2016-12-14 | 2
Q3-00090 | Leak test and pressure test | Hall C Tech | Labor | 2016-12-13 | 2016-12-13 | 1
Q2-00165 | Acceptance Test | Hall C Tech | Labor | 2016-12-13 | 2017-01-04 | 10
Q2-00165 | Acceptance Test | SigmaPhi | Nonlabor | 2016-12-13 | 2017-01-04 | 10
Q3-00095 | N2 gas purge magnet helium circuit | Alignment Tech | Labor | 2016-12-14 | 2016-12-16 | 3
Q3-00047 | Install AC Power for top of CCR | ELEC TECH ELECTRICIAN | Labor | 2016-12-15 | 2016-12-16 | 4
Dipole-00145 | Apply Inner MLI | Hall C Tech | Labor | 2016-12-15 | 2016-12-15 | 0.5
Dipole-00150 | Install Shield | Hall C Tech | Labor | 2016-12-15 | 2016-12-15 | 1.5
Dipole-00175 | N2 gas purge magnet helium circuit | Hall C Tech | Labor | 2016-12-15 | 2016-12-16 | 1
Q3-00070 | Install relief valve tree | Hall C Tech | Labor | 2016-12-15 | 2016-12-15 | 2
Dipole-00155 | Apply outer MLI | Hall C Tech | Labor | 2016-12-16 | 2016-12-16 | 0.5
Dipole-00160 | Install and weld one pass chimney | Hall C Tech | Labor | 2016-12-16 | 2016-12-20 | 2
Q3-00075 | Install CCR Top Hardware | Hall C Tech | Labor | 2016-12-16 | 2016-12-19 | 2
Dipole-00160 | Install and weld one pass chimney | Hall C Welder | Labor | 2016-12-16 | 2016-12-20 | 2
Q3-00050 | Dress I&C Feedthrus | Spec Support Group | Labor | 2016-12-16 | 2016-12-19 | 2
Beam-00025 | ARR Prep Work | Hall C Engineer | Labor | 2016-12-19 | 2017-01-09 | 5
Q3-00060 | Check out I&C | Hall C Engineer | Labor | 2016-12-20 | 2017-01-03 | 4
Q3-00055 | Connect I&C cables | Hall C Tech | Labor | 2016-12-20 | 2017-01-03 | 4
Q3-00060 | Check out I&C | Hall C Tech | Labor | 2016-12-20 | 2017-01-03 | 4
Q3-00080 | Calibrate JT Valves | Hall C Tech | Labor | 2016-12-20 | 2016-12-21 | 2
Dipole-00185 | Magnet pump down | Hall C Tech | Labor | 2016-12-20 | 2016-12-25 | 1
Dipole-00190 | Leak test and pressure test | Hall C Engineer | Labor | 2017-01-03 | 2017-01-03 | 1
Dipole-00210 | Connect N2 gas vent line, warm He return line | Hall C Tech | Labor | 2017-01-03 | 2017-01-03 | 2
Dipole-00190 | Leak test and pressure test | Hall C Tech | Labor | 2017-01-03 | 2017-01-03 | 1
Dipole-00215 | Install Lead gas return lines | Hall C Tech | Labor | 2017-01-04 | 2017-01-06 | 6
Dipole-00195 | Vent vacuum to N2 Gas | Hall C Tech | Labor | 2017-01-04 | 2017-01-04 | 0.1
Q3-00100 | Connect DC water cooled Bus | Hall C Tech | Labor | 2017-01-04 | 2017-01-04 | 1
Dipole-00200 | Complete chimney welding | Hall C Tech | Labor | 2017-01-04 | 2017-01-06 | 2
Dipole-00200 | Complete chimney welding | Hall C Welder | Labor | 2017-01-04 | 2017-01-06 | 2
Q3-00100 | Connect DC water cooled Bus | Spec Support Group | Labor | 2017-01-04 | 2017-01-04 | 2
Q3-00105 | Connect N2 gas vent line, warm He return line | Hall C Tech | Labor | 2017-01-05 | 2017-01-05 | 2
Dipole-00205 | Final Pump down vacuum | Hall C Tech | Labor | 2017-01-06 | 2017-01-10 | 2
Q3-00110 | Install Lead gas return lines | Hall C Tech | Labor | 2017-01-06 | 2017-01-10 | 6
Dipole-00220 | Leak test Helium gas lines and lead return line | Hall C Tech | Labor | 2017-01-09 | 2017-01-09 | 1
Beam-00035 | ARR Response to Recomendations | Hall C Engineer | Labor | 2017-01-10 | 2017-01-18 | 5
Dipole-00225 | Pump and purge helium circuit | Hall C Tech | Labor | 2017-01-10 | 2017-01-11 | 2
Q3-00115 | Leak test Helium gas lines and lead return line | Hall C Tech | Labor | 2017-01-11 | 2017-01-11 | 1
Dipole-00230 | Circulate warm He gas thru magnet | ESR operator | Labor | 2017-01-12 | 2017-01-13 | 0.4
Dipole-00230 | Circulate warm He gas thru magnet | Hall C Tech | Labor | 2017-01-12 | 2017-01-13 | 2
Q3-00120 | Pump and purge helium circuit | Hall C Tech | Labor | 2017-01-12 | 2017-01-13 | 2
Dipole-00240 | Insert U-tubes | ESR operator | Labor | 2017-01-17 | 2017-01-17 | 1
Q3-00125 | Circulate warm He gas thru magnet | ESR operator | Labor | 2017-01-17 | 2017-01-18 | 2
Q3-00125 | Circulate warm He gas thru magnet | Hall C Tech | Labor | 2017-01-17 | 2017-01-18 | 2
Dipole-00240 | Insert U-tubes | Hall C Tech | Labor | 2017-01-17 | 2017-01-17 | 3
Dipole-00247 | Final Alignment | Alignment Tech | Labor | 2017-01-18 | 2017-01-20 | 6
Dipole-00245 | Cool down Dipole to 80 K | Hall C Engineer | Labor | 2017-01-18 | 2017-02-01 | 1
Beam-00010 | Install Vac. Extension w/Shutter OR NGC | Hall C Tech | Labor | 2017-01-18 | 2017-01-24 | 2
Dipole-00247 | Final Alignment | Hall C Tech | Labor | 2017-01-18 | 2017-01-20 | 6
Q3-00135 | Insert U-tubes | ESR operator | Labor | 2017-01-19 | 2017-01-19 | 1
Q3-00130 | Install Q2-Q3 and Q3-Dipole vacuum tube | Hall C Tech | Labor | 2017-01-19 | 2017-01-20 | 4
Q3-00135 | Insert U-tubes | Hall C Tech | Labor | 2017-01-19 | 2017-01-19 | 2
Q3-00142 | Final Alignment | Alignment Tech | Labor | 2017-01-20 | 2017-01-24 | 6
Q3-00140 | Cool down to 80 K | Hall C Engineer | Labor | 2017-01-20 | 2017-01-29 | 1
Q3-00142 | Final Alignment | Hall C Tech | Labor | 2017-01-20 | 2017-01-24 | 6
Dipole-00248 | Initial Quench Detector Settings | Hall C Engineer | Labor | 2017-01-23 | 2017-01-23 | 1
Dipole-00235 | Install Q3-D vacuum tube | Hall C Tech | Labor | 2017-01-23 | 2017-01-24 | 2
Dipole-00249 | Install Electrical Shields on top of CCR | Hall C Tech | Labor | 2017-01-23 | 2017-01-24 | 1
Q3-00143 | Initial Quench Detector Settings | Hall C Engineer | Labor | 2017-01-25 | 2017-01-25 | 1
Beam-00012 | Install Final Roof and Wall Blocks | Hall C Tech | Labor | 2017-01-25 | 2017-01-25 | 4
Q3-00144 | Install Electrical Shields on top of CCR | Hall C Tech | Labor | 2017-01-25 | 2017-01-26 | 1
Beam-00015 | Install & Leak-Check Beam Pipes DS of Tgt | Hall C Tech | Labor | 2017-01-26 | 2017-02-01 | 2
Q3-00145 | Helium fill Q3 | ESR operator | Labor | 2017-01-30 | 2017-01-31 | 2
Q3-00145 | Helium fill Q3 | Hall C Engineer | Labor | 2017-01-30 | 2017-01-31 | 2
Q3-00150 | Adjust controls | Hall C Engineer | Labor | 2017-01-30 | 2017-01-31 | 1
Q3-00150 | Adjust controls | Hall C Tech | Labor | 2017-01-30 | 2017-01-31 | 2
Q3-00155 | Low power testing ~ 10 % | Hall C Engineer | Labor | 2017-02-01 | 2017-02-02 | 4
Q3-00155 | Low power testing ~ 10 % | Hall C Tech | Labor | 2017-02-01 | 2017-02-02 | 2
Q3-00155 | Low power testing ~ 10 % | SigmaPhi | Nonlabor | 2017-02-01 | 2017-02-02 | 2
Dipole-00250 | Helium fill Dipole | ESR operator | Labor | 2017-02-02 | 2017-02-06 | 0.8
Dipole-00250 | Helium fill Dipole | Hall C Engineer | Labor | 2017-02-02 | 2017-02-06 | 3
Dipole-00255 | Adjust Cryo controls | Hall C Engineer | Labor | 2017-02-02 | 2017-02-06 | 3
Q3-00160 | Progressive testing and support adjustment | Hall C Engineer | Labor | 2017-02-03 | 2017-02-09 | 20
Q3-00160 | Progressive testing and support adjustment | Hall C Tech | Labor | 2017-02-03 | 2017-02-09 | 10
Q3-00160 | Progressive testing and support adjustment | SigmaPhi | Nonlabor | 2017-02-03 | 2017-02-09 | 5
Dipole-00260 | Low power testing ~ 10 % | Hall C Engineer | Labor | 2017-02-07 | 2017-02-08 | 4
Dipole-00260 | Low power testing ~ 10 % | Hall C Tech | Labor | 2017-02-07 | 2017-02-08 | 2
Dipole-00260 | Low power testing ~ 10 % | SigmaPhi | Nonlabor | 2017-02-07 | 2017-02-08 | 2
Dipole-00265 | Progressive testing and support adjustment | Hall C Engineer | Labor | 2017-02-09 | 2017-02-15 | 20
Dipole-00265 | Progressive testing and support adjustment | Hall C Tech | Labor | 2017-02-09 | 2017-02-15 | 10
Dipole-00265 | Progressive testing and support adjustment | SigmaPhi | Nonlabor | 2017-02-09 | 2017-02-15 | 5
Q3-00165 | Acceptance Test | Hall C Engineer | Labor | 2017-02-10 | 2017-02-16 | 20
Q3-00165 | Acceptance Test | Hall C Tech | Labor | 2017-02-10 | 2017-02-16 | 10
Q3-00165 | Acceptance Test | SigmaPhi | Nonlabor | 2017-02-10 | 2017-02-16 | 5
Dipole-00270 | Dipole Full-Field Testing | Hall C Engineer | Labor | 2017-02-16 | 2017-02-22 | 20
Dipole-00270 | Dipole Full-Field Testing | Hall C Tech | Labor | 2017-02-16 | 2017-02-22 | 10
Dipole-00270 | Dipole Full-Field Testing | SigmaPhi | Nonlabor | 2017-02-16 | 2017-02-22 | 5
Beam-00020 | Complete Power-test of All Magnets Together | Hall C Engineer | Labor | 2017-02-23 | 2017-02-23 | 1
Beam-00040 | Commisioning with Beam | Hall C Contributed University Labor | Labor | 2017-02-24 | 2017-03-02 | 63
Beam-00040 | Commisioning with Beam | Hall C Engineer | Labor | 2017-02-24 | 2017-03-02 | 20.5
Beam-00040 | Commisioning with Beam | Hall C Scientist | Labor | 2017-02-24 | 2017-03-02 | 49
Beam-00040 | Commisioning with Beam | Hall C Tech | Labor | 2017-02-24 | 2017-03-02 | 3.5
Beam-00040 | Commisioning with Beam | Hall C Visiting User | Labor | 2017-02-24 | 2017-03-02 | 42
Q2-00010 | Transport into Hall C | Lockwood | Nonlabor | 06-Oct-16 A | 2016-10-06 | 1
Dipole-00005 | Magnet ERR Preperations | Hall C Engineer | Labor | 20-Sep-16 A | 2016-10-11 | 1

## Sheet2
LN2 | Offset -> | 0
| Engineering Value | V | Test Pressure psig | Test pressure AMTG | Pressure Calculated | Atm (ABS)
| 1.7178 | 0.83959 | 5 | 0.34023 | 0.34 | 1.3402
| 5.1535 | 2.4537 | 15 | 1.0207 | 1.02 | 2.0207
| 13.7428 | 6.516 | 40 | 2.7218 | 2.72 | 3.7218
He | Offset -> | 0
| Engineering Value | V | Test Pressure psig | Test pressure AMTG | Pressure Calculated | Atm (ABS)
| 1.7178 | 0.473 | 5 | 0.34023 | 0.34 | 1.3402
| 5.1535 | 2.1481 | 15 | 1.0207 | 1.02 | 2.0207
| 13.7428 | 6.469 | 40 | 2.7218 | 2.72 | 3.7218